## Cover Page
Food Delivery App
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | 1. Piyush Das, 2. Ashutosh Mishra, 3. Kanha Sahu, 4. Deviprasad Dash
| Role | Programmer Analyst Trainee
Signature
| Date | 05-08-2025
Project ID: POD5 | POD 3 |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Project ID: POD3 <Food Delivery App> C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_01 | Customer Registration | New User | As a new user, I want to register so I can place food orders. | Registration form with Name, Email, Phone, Password. Validations for required fields and email format. Data stored in Customer table. Success message on registration. Error for duplicate email or invalid input. | High | 3 | Yes
US_02 | Customer Login | Registered User | As a registered user, I want to log in securely to access my dashboard. | Login form with Email and Password. JWT-based authentication. Error message for invalid credentials. Redirect to dashboard on successful login. Session maintained securely. | Critical | 3 | Yes
US_03 | Profile Management | Registered User | As a user, I want to view and update my profile details so that I can keep my information up to date. | Editable profile page with form validation. Updates are reflected in the database upon submission. | High | 5 | Yes
US_04 | Add Menu Items | Restaurant Owner | As a restaurant owner, I want to add new food items to my menu so that customers can see and order them. | Form includes item name, description, price, and image upload. Data is validated and stored in the database. | Critical | 8 | Yes
US_05 | Update/Delete Menu Items | Restaurant Owner | As a restaurant owner, I want to update or remove menu items so that I can manage my offerings effectively. | CRUD operations are available with confirmation prompts for update and delete actions. Changes are reflected in the database. | High | 3 | Yes
US_06 | View Menu | End User | As a customer, I want to browse the restaurant’s menu so that I can decide what to order. | Menu is displayed responsively with food items grouped by category. Filters are available. Data is fetched from backend API. | Critical | 5 | Yes
US_07 | Place Order | End User | As a customer, I want to place an order for selected items so that I can receive my food. | Cart functionality allows item selection and quantity adjustment. Order summary is shown before confirmation. Order is stored in the database. | Critical | 8 | Yes
US_08 | Track Order Status | End User | As a customer, I want to track the status of my order so that I know when it will arrive. | Real-time updates are shown for order status transitions: Pending → Accepted → Delivered. Status is fetched from backend and displayed clearly. | High | 3 | Yes
US_09 | Cancel Order | End User | As a customer, I want to cancel an order before it’s prepared so that I’m not charged unnecessarily. | Cancellation is allowed only when the order status is “Pending.” Cancel button is visible conditionally. Status update is reflected in backend. | High | 5 | Yes
US_10 | Assign Delivery Agent | System | As System, it assign delivery agents to orders so that deliveries are handled efficiently. | System assign delivery agents. Assignment is stored in the database and reflected in order details. | High | 5 | Yes
US_11 | Update Delivery Status | Restaurant Owner | As a restaurant owner, I want to update the delivery progress so that the system reflects the current status. | Restaurant owner can select status options: In Progress, Delivered. Updates are stored in the backend and visible to customer and admin. | High | 3 | Yes
US_13 | Make Payment | End User | As a customer, I want to pay for my order using various methods so that I can complete my purchase conveniently. | After payment success and failure handling with appropriate messages. | High | 5
US_14 | View Payment History | End User | As a customer, I want to view my past payments so that I can track my spending. | List of transactions with status, amount, and date. Filter by date range. | Medium | 3

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000