## Cover Page
Food Delivery App
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Piyush Das, Ashutosh Mishra, Kanha Sahu, Deviprasad Dash
| Role | Programmer Analyst Trainee
Signature
| Date | 05-08-2025
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/.
Sprint 1/2
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog - Sprint Backlog C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO |  | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | Customer Registration | 3
Task_1 | Create Customer entity & repository |  | Deviprasad Dash | Completed | 6 | 5 | 2 | 0.5 | 0 | 0
Task_2 | Implement registration logic with validation |  | Deviprasad Dash | Completed | 5 | 4 | 0 | 0.5 | 0 | 0
Task_3 | Handle duplicate email error |  | Deviprasad Dash | Completed | 4 | 1 | 2 | 1 | 0.5 | 0
US_2 | Customer Login | 3
Task_1 | Setup JWT-based authentication |  | Deviprasad Dash | Completed | 6 | 5 | 1 | 1 | 1 | 0
Task_2 | Create login controller & services |  | Deviprasad Dash | Completed | 6 | 4 | 0 | 0 | 1 | 0
US_3 | Profile Management | 5
Task_1 | Create API to fetch/update profile |  | Deviprasad Dash | Completed | 7 | 1 | 0 | 2 | 2 | 1
US_4 | Add Menu Items | 8
Task_1 | Create MenuItem entity & upload controller |  | Kanha Sahu | Completed | 6 | 5 | 2 | 1 | 0.5 | 0.5
Task_2 | Handle image storage and validation |  | Kanha Sahu | Completed | 6 | 2 | 0 | 2 | 1 | 1
US_5 | Update/Delete Menu Items | 3
Task_1 | Implement update item endpoint |  | Kanha Sahu | Completed | 6 | 4 | 2 | 2 | 0 | 0
Task_2 | Implement delete item with confirmation |  | Kanha Sahu | Completed | 5 | 3 | 2 | 2 | 2 | 0
US_6 | View Menu | 5
Task_1 | Build API to fetch menu by category |  | Kanha Sahu | Completed | 5 | 1 | 2 | 2 | 1 | 0
US_7 | Place Order | 8
Task_1 | Create Order entity and cart logic |  | Ashutosh Mishra | Completed | 5 | 0 | 0 | 3 | 2 | 2
Task_2 | Store orders in DB and generate summary |  | Ashutosh Mishra | Completed | 6 | 5 | 1 | 1 | 1 | 0
US_8 | Track Order Status | 3
Task_1 | Implement order status update API |  | Ashutosh Mishra | Completed | 6 | 5 | 1 | 1 | 1 | 0
Task_2 | Expose status API for frontend polling |  | Ashutosh Mishra | Completed | 6 | 4 | 0 | 0 | 1 | 0
US_9 | Cancel Order | 5
Task_1 | Add cancel order condition check (Pending) |  | Ashutosh Mishra | Completed | 6 | 5 | 2 | 1 | 0.5 | 0.5
Task_2 | Update status on cancel |  | Ashutosh Mishra | Completed | 6 | 2 | 0 | 2 | 1 | 1
US_10 | Assign Delivery Agent | 5
Task_1 | Implement delivery agent assignment logic |  | Ashutosh Mishra | Completed | 5 | 0 | 0 | 3 | 2 | 2
US_11 | Update Delivery Status | 3
Task_1 | Endpoint to update delivery progress |  | Ashutosh Mishra | Completed | 5 | 4 | 0 | 0.5 | 0 | 0
US_12 | Make Payment | 5
Task_1 | Integrate payment gateway backend API |  | Piyush Das | Completed | 5 | 0 | 0 | 3 | 2 | 2
Task_2 | Handle payment success/failure response |  | Piyush Das | Completed | 6 | 5 | 1 | 1 | 1 | 0
US_13 | View Payment History | 3
Task_1 | Fetch transaction list from database |  | Piyush Das | Completed | 6 | 5 | 1 | 1 | 1 | 0
Task_2 | Implement date-range filter logic |  | Piyush Das | Completed | 6 | 4 | 0 | 0 | 1 | 0
TOTAL |  | 59 |  |  | 130 | 74 | 19 | 30.5 | 22.5 | 10

## Sprint 2
Sprint Backlog - Sprint Backlog C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO |  | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | Customer Registration | 3
Task_1 | Build registration form with validation |  | Deviprasad Dash | Completed | 6 | 5 | 2 | 0.5 | 0 | 0
Task_2 | Show success/error messages |  | Deviprasad Dash | Completed | 5 | 4 | 0 | 0.5 | 0 | 0
US_2 | Customer Login | 3
Task_1 | Design login form UI |  | Deviprasad Dash | Completed | 6 | 5 | 1 | 1 | 1 | 0
Task_2 | Integrate login API & manage token |  | Deviprasad Dash | Completed | 6 | 4 | 0 | 0 | 1 | 0
US_3 | Profile Management | 5
Task_1 | Profile form and data binding |  | Deviprasad Dash | Completed | 7 | 1 | 0 | 2 | 2 | 1
Task_2 | API integration for update |  | Deviprasad Dash | Completed | 6 | 2 | 0 | 2 | 1 | 1
US_4 | Add Menu Items | 8
Task_1 | Form UI for adding item |  | Kanha Sahu | Completed | 6 | 5 | 2 | 1 | 0.5 | 0.5
Task_2 | Image upload integration |  | Kanha Sahu | Completed | 6 | 2 | 0 | 2 | 1 | 1
US_5 | Update/Delete Menu Items | 3
Task_1 | Create UI for item update/delete |  | Kanha Sahu | Completed | 6 | 4 | 2 | 2 | 0 | 0
Task_2 | Confirmation prompt handling |  | Kanha Sahu | Completed | 5 | 3 | 2 | 2 | 2 | 0
US_6 | View Menu Items | 5
Task_1 | Display menu items with filters |  | Kanha Sahu | Completed | 5 | 1 | 2 | 2 | 1 | 0
US_7 | Place Order | 8
Task_1 | Cart UI and quantity management |  | Ashutosh Mishra | Completed | 5 | 0 | 0 | 3 | 2 | 2
Task_2 | Show order summary and place order |  | Ashutosh Mishra | Completed | 6 | 5 | 1 | 1 | 1 | 0
US_8 | Track Order Status | 3
Task_1 | Order tracking UI with live status updates |  | Ashutosh Mishra | Completed | 6 | 5 | 1 | 1 | 1 | 0
US_9 | Cancel Order | 5
Task_1 | Add cancel button (conditional) |  | Ashutosh Mishra | Completed | 6 | 5 | 2 | 1 | 0.5 | 0.5
Task_2 | Integrate with cancel order API |  | Ashutosh Mishra | Completed | 6 | 2 | 0 | 2 | 1 | 1
US_10 | Assign Delivery Agent | 5
Task_1 | Show delivery agent info in order details |  | Ashutosh Mishra | Completed | 5 | 0 | 0 | 3 | 2 | 2
US_11 | Update Delivery Status | 3
Task_1 | Delivery status dropdown for restaurant owner |  | Ashutosh Mishra | Completed | 5 | 4 | 0 | 0.5 | 0 | 0
US_12 | Make Payment | 5
Task_1 | Payment form UI with options |  | Piyush Das | Completed | 5 | 0 | 0 | 3 | 2 | 2
Task_2 | Handle payment response display |  | Piyush Das | Completed | 6 | 5 | 1 | 1 | 1 | 0
US_13 | View Payment History | 3
Task_1 | List past payments with filters |  | Piyush Das | Completed | 6 | 5 | 1 | 1 | 1 | 0
TOTAL |  | 59 |  |  | 120 | 67 | 17 | 31.5 | 22 | 11

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55

## Data (hidden)
In-Progress
Completed
N/A